## Checklist
Weekend Planner
Item | Responsible | Next Step | Due Date | Complete (Y/N) | Consider
Determine venue, dates |  | Rent, lease, etc. |  |  | Avoid overlapping events
Set event budget |  | Registration fee |  |  | Housing, food, activities
Decide on a theme |  | Assign speakers |  |  | Activity & topic choice
Build registration site* |  | Create QR code |  |  | Payment method & date
Assign responsibilities |  | Planning meeting |  |  | See chart below
Schedule |  | Create brochure
Advertise event** |  | Social media |  |  | Announcement, fliers
Registration |  | Send schedule |  |  | Arranging transportation
Lodging (if applicable) |  | Notify attendees |  |  | Assign rooms
Purchase supplies |  |  |  |  | Reimburse as appropriate
Responsibilities
Item | Responsible | Details
Coordinator(s)
Brochure |  | Consider schedule, address, map
Setup crew |  | Perform pre-clean
Food |  | Consider also: coffee station, hot chocolate, etc.
Menu
Crew members
Presenters |  | Consider assigning a book to read prior; communicate this beforehand
Activities (see below)
Friday |  | Consider name tags, lanyards
Sabbath |  | Sabbath services: assign songleader, speakers, special music, etc.
Saturday night
Sunday
Monday
Sound sytem |  | Decide who will bring equipment, set up, run, etc.
Photographer
Cleanup crew |  | Perform post-clean
Notes:
*RegFox and Webconnex are some popular options for registration forms. Contact david_browning@ucg.org for assistance. Create a coupon code at this time for a discounted early registration or free registration for presenters.
**In addition to fliers and social media, reach out to uya@ucg.org to advertise in the young adult newsletter, chris_rowland@ucg.org to include in the Home Office Weekly Update or un@ucg.org to advertise in United News or on the members’ website.

## Schedule
Instructions: Use this as a sample schedule and edit it to fit your needs.
Schedule
Friday |  | Sunday
Time | Activity | Time | Activity
4:00 p.m. | Arrival | 8:00 a.m. | Breakfast
6:00 p.m. | Dinner | 9:00 a.m. | Presentation 5
7:00 p.m. | Icebreaker | 10:00 a.m. | Activity
8:00 p.m. | Presentation 1 | 12:00 p.m. | Lunch
|  | 1:00-3:00 p.m. | Activity
|  | 3:30 p.m. | Hike
|  | 6:00 p.m. | Dinner
|  | 7:00 p.m. | Campfire
Sabbath |  | Monday
Time | Activity | Time | Activity
8:30 a.m. | Breakfast | 8:00 a.m. | Breakfast
10:30 a.m. | Church Services | 9:00 a.m. | Camp Clean Up
1:30 p.m. | Lunch | 11:00 a.m. | Checkout
3:00 p.m. | Presentation 2
4:00 p.m. | Presentation 3
5:00 p.m. | Presentation 4
6:00 p.m. | Dinner
7:00 p.m. | Game Night

## Presentations
Instructions: Use this sheet to assign and track progress of presentations and activities before your weekend.
Presentation Plan
| Presenter/Coordinator | Assistant(s) | Idea Meeting | Outline | Review Meeting (Presentations) | Dry Run | Full Run
Presentation 1
Presentation 2
Presentation 3
Presentation 4
Presentation 5
Friday Night Icebreaker
Saturday Night
Special Music
Song Leading
Sermon #1
Sermon #2
Sunday Activities
Monday Activities

## Budget
Instructions: Use this sheet to keep track of your budget. Replace the sample text with your own weekend details.
Budget
Item | Cost per person | # Persons | Total | Actual Cost | Variance
Rooms (per bed) | 75 | 50 | 3750 | 3924.51 | -174.51
Hall rental |  |  | 5000 | 5025.52 | -25.52
Food | 200 | 50 | 10000 | 9843.68 | 156.32
Sunday Activity | 17 | 32 | 544 | 555.06 | -11.06
Monday Activity | 13 | 43 | 559 | 508.68 | 50.32
Promotion |  |  | 47 | 47.59 | -0.59
Supplies |  |  | 73 | 71.23 | 1.77
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
Totals: |  |  | 19973 | 19976.27 | -3.27

## Transportation
Instructions: Use this sheet to keep track of the transportation needs of weekend attendees.
Transportation Plan
Name | Arrival Time/Airline | Ride | Departure Time/Airline | Ride
Person 1 | 8/6/24 American 6:30 p.m. | Driver 1 | 9/2/24 Delta 1:30 p.m. | Driver 2

## Registration
Registrant Information | [9 empty] | Activities |  |  |  |  | Travel |  | Service Areas |  |  |  | Additional Information |  | Payment
First Name | Last Name | Gender | Marital Status | Phone Number | Email | Home Congregation | (State) | (ZIP/Postal Code) | Base Registration Cost ($ Amount) | Registration Options | Activity #1 | Activity #2 | Activity #3 | Cost of Selected Activities ($ Amount) | Will you be flying in for the weekend? (Y/N) | Comments | Special Music (Y/N) | Photographer (Y/N) | (Set up/take down) | (Presentation) | Any food allergies or dietary restrictions? | Would you like to share topics for discussion, or have any questions? | Total Cost ($ Amount) | Coupon Code ($ Amount) | Coupon Code (Code) | Amount Due ($ Amount)
Sample | Presenter | Male | Single | 15208480182 | first.last@gmail.com | Phoenix Northwest | AZ | 85331 | 165 | Friday Feb 23 - Monday, Feb 26 | Yes | No | Yes | 25 | No; driving |  | Yes |  | Yes | Yes |  |  | 190 | 165 | FLAME2024 | 25